## Sprint1
Timeline
Who | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Nic | Working on getting ignition software to work and loaded for other group members | Software working, started working on front end design tabs needed | Overall structure laid out, started working on input fields for reading member ID and adding items to sales interface | Sales interface working, some trouble encountered with displaying the sales, it keeps diaplying old sales, will continue working on it | Sales interface working well, minor issues with some records, need to implement input sanitisation (no negative numbers etc) | Input sanitisation still not working, moved buttons to better use the space on sales interface. | Making confirm button for sales interface, coding in python. | Still working on confirm button. | Confirm button complete, helping replicate code for other group members. | Minor changes to UI, tab buttons, added page for reports to be done in Sprint 2.
Dylan | Creating documentation for the group | Documentation created successfully, make sure member table autoincrements as new records are put into it | Member table autoincrements, started work on visual interface to display the member table when on the member page | Member viewport working, helped other memebers recycle that slab of code, start work on search interface for members | Search interface complete but only refreshes every 5 seconds, more work needed to make it filter in live time. | Lowered refresh rate, still couldn't get it to ONLY refresh upon change, which would be ideal. | Confirm button for member table finished. | Busy on other assignments | Designing imporved UI components with Nic, code review to make sure all buttons working. | Helping with cosmetic changes and testing.
Simon | Developing SQL queries, specifically create for Sales Table | Sales table created, develop add and delete SQL queries | Sales table complete with all SQL functions, started work on search field to find members by ID from table | Could not get search field working, continuing work, Dylan may be able to help. | Search field working, same issue as above. | Search field working. Working on modification UI. | Modification UI half working, some of the fields won't populate, need to have a look at the porper syntax. | Modification fields now populate correctly. | Busy with other assignments. | All tasks complete. Testing.
Cody | Developing SQL queries, specifically create for Sales Table | Sales table created, design visual for interactive sales interface | Visual deign completed, working with Nic to create interface button to simulate a sale | Interface buttons working well, now to create the confirm button which will push all the queries and data into table | Still working on confirm button, data is pushed but needs timestamp in order to be properly displayed | Added timestamps to tables, will do for others. | Added timestamps to all tables, working on filtering display by timestamp, so outdated orders are not displayed. | Display not quite working, syntax is difficult to work with. Working with Rabya to make it work. | Sales display table working, have to make price display with a dollar sign. | Dollar sign displayed.
Thomas | Developing SQL queries, specifically create for Item Table | Item table created, creating SQL for add, delete and modify items | Item table complete, working with Dylan to develop a viewport which will display the list of items. | Item viewport working, working on clicking an item to prepoulate the item fields and modify. | Item modification working, interface needs work becasuse it's not intuitive, working on confirm button to push SQL queries | Still working on confirm button. | Busy with other assignments. | Finished confirm button, interface testing to make sure all the buttons work as intended. | All tasks complete. Testing. | All tasks complete. Testing.
Rabya | Developing SQL queries, specifically create for member table | Member table created, making SQL for adding, deleting and modifying members | Member table complete with all SQL, working with Thomas on the display viewport | Trying to develop the same function where clicking on a member prepoulates fields allowing for modification | Working on confirm button as well | Member prepopulated fields working well, tested thoroughly. | Confirm button finished, member UI | Helping Cody work on the timestamp filtering for disaply views. | Timestamp filtering working. Now to work on, | All tasks complete. Testing.

## Sprint2
Timeline
Who | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Nic | Researching ignition pdf outputting system for reports | Adding UI features for pdf reporting | Adding UI features for viewing member sales report, going to do it through reports | Implemented a little bit of mock data into database to start generating quality reports | With fresh data, viewing tables bit cluttered, implemented a search function | Worked on the start and end date brackets for report generating | Finished the start and end date brackets for report generating | Start implementating stock recomendation | Implementation of low stock inventory trigger with Dylan | Testing
Dylan | Researching potential stock prediction algo | Decided on a simple low-stock trigger, will look into automatically working out sales of a given item | Created large sets of mock data to be implmeneted into the system | Other subject commitments | Documentation, prepared the tasks for submission | Continued implementing mock data | Continued implementing mock data | Other subject commitments | Implementation of low stock inventory trigger | Testing, testing and more testing, also documentation for submission
Simon | Started to implement UI feature changes | Other subject commitments | Played with implmeneting a more clear edit member button which highlights input fields etc. | Tried to implment moving average trigger for low stock. | Testing of moving average script, probably will have to use a different metric | Other subject commitments | Started linking button scripting for report generation | Worked on auto report generation so that they automatically create reports every 24 hours etc | Review of report layout, specifically the pdf form | Implemented minor changes to report output
Cody | Learning about SQL for CSV outputs | Adding UI features for csv reporting | Adding UI features for pdf reporting | Bugfixing and testing, sometimes report bracket snot registering correctly | Other subject commitments | Worked on report output for pdf report, formatting etc | Continued formatting of pdf reports, specific attention to graphical components | Other subject commitments | Added UI components to the POS interface which remove a selected item or the entire order, more flexible than before | Added UI option to ammend order as well to the POS system
Thomas | Sketch prototype UI | Started implementing UI changes | Continued implementing UI changes | Other subject commitments | Final retry of UI sketch | Finshed UI design | Other subject commitments | Worked on auto report generation at timed intervals, research timestamp datatypes | Minor changes to UI positioning, especially tab navigation between the panels | UI usability testing
Rabya | Learning about SQL for CSV outputs | Writing code for processing the SQL and outputting as csv | Finalised and implemented code for csv report generation, tested on data | Bugfixing and testing | Other subject commitments | Implemented auto report generation for csv, so it generates at the same time as the pdf reports | Other subject commitments | Reviewed CSV output formatting and made sure all data is represented using mock data | Fixed input bugs where a negative input would cause the inventory level to increase | UI usability testing