## Sheet1
Timeline
Who | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Nic | Timeline Day 1: Working on getting ignition software to work and loaded for other group members; Timeline Day 2: Software working, started working on front end design tabs needed; Timeline Day 3: Overall structure laid out, started working on input fields for reading member ID and adding items to sales interface; Timeline Day 4: Sales interface working, some trouble encountered with displaying the sales, it keeps diaplying old sales, will continue working on it; Timeline Day 5: Sales interface working well, minor issues with some records, need to implement input sanitisation (no negative numbers etc)
Dylan | Timeline Day 1: Creating documentation for the group; Timeline Day 2: Documentation created successfully, make sure member table autoincrements as new records are put into it; Timeline Day 3: Member table autoincrements, started work on visual interface to display the member table when on the member page; Timeline Day 4: Member viewport working, helped other memebers recycle that slab of code, start work on search interface for members; Timeline Day 5: Search interface complete but only refreshes every 5 seconds, more work needed to make it filter in live time.
Simon | Timeline Day 1: Developing SQL queries, specifically create for Sales Table; Timeline Day 2: Sales table created, develop add and delete SQL queries; Timeline Day 3: Sales table complete with all SQL functions, started work on search field to find members by ID from table; Timeline Day 4: Could not get search field working, continuing work, Dylan may be able to help.; Timeline Day 5: Search field working, same issue as above.
Cody | Timeline Day 1: Developing SQL queries, specifically create for Sales Table; Timeline Day 2: Sales table created, design visual for interactive sales interface; Timeline Day 3: Visual deign completed, working with Nic to create interface button to simulate a sale; Timeline Day 4: Interface buttons working well, now to create the confirm button which will push all the queries and data into table; Timeline Day 5: Still working on confirm button, data is pushed but needs timestamp in order to be properly displayed
Thomas | Timeline Day 1: Developing SQL queries, specifically create for Item Table; Timeline Day 2: Item table created, creating SQL for add, delete and modify items; Timeline Day 3: Item table complete, working with Dylan to develop a viewport which will display the list of items.; Timeline Day 4: Item viewport working, working on clicking an item to prepoulate the item fields and modify.; Timeline Day 5: Item modification working, interface needs work becasuse it's not intuitive, working on confirm button to push SQL queries
Rabya | Timeline Day 1: Developing SQL queries, specifically create for member table; Timeline Day 2: Member table created, making SQL for adding, deleting and modifying members; Timeline Day 3: Member table complete with all SQL, working with Thomas on the display viewport; Timeline Day 4: Trying to develop the same function where clicking on a member prepoulates fields allowing for modification; Timeline Day 5: Working on confirm button as well