## Sprint 1
Num | Level | Product | Item | Description | Prerequisites | Team Member | Est. Time | Actual Time
1 | Critical | Inventory Table | Create Item Table | Item table with data validation - NOT NULL, etc - which records item details for company inventory | - | Dylan | 0.3
2 | Major | Inventory Table | Create Queries to Add Item | Simple query to add item, will be triggered by visual fields on the UI | 1 | Dylan | 0.3
3 | Minor | Inventory Table | Create Queries to Delete Item | Simple query to delete item, will be triggered by visual fields on the UI | 1 | Dylan | 0.3
4 | Minor | Inventory Table | Create Queries to Modify Item | Simple query to modify item, will be triggered by visual fields on the UI | 1-2 | Dylan | 0.3
5 | Critical | Member Table | Create Member Table | Member table with data validation - NOT NULL, etc - which records member details | - | Dylan | 0.3
6 | Critical | Member Table | Create Queries to Add Member | Simple query to add member, will be triggered by visual fields on the UI | 5 | Dylan | 0.3
7 | Minor | Member Table | Create Queries to Delete Member | Simple query to delete member, will be triggered by visual fields on the UI | 5 | Dylan | 0.3
8 | Minor | Member Table | Create Queries to Modify Member | Simple query to modify member, will be triggered by visual fields on the UI | 5-6 | Dylan | 0.3
10 | Critical | Sales Record Table | Create Sales Table | Sales table with references to both the items and members table | - | Dylan | 0.5
11 | Critical | Sales Record Table | Create Query to Add Sale | Simple Query to add sale, will be triggered by UI interface basically simulating a POS machine. When sale is added inventory of the item should decreas by the amount bought | 1, 10 | Dylan | 0.3
12 | Critical | Add Sales Record UI | Input Field to Add Member ID | Member ID must be added before any items such that each item can be associated with the correct member in the sales table | 10-11 | Cody | 4
13 | Major | Add Sales Record UI | Buttons to Add Different Items to Sale | Buttons simulate the effect of a barcode being scanned or similar, adding | 10-12 | Cody | 4
14 | Critical | Add Sales Record UI | Button to Confirm Sale | Pushes all sales records to the sales table, trigger the decrementing inventory for given items | 11-12 | Nic | 2
15 | Major | Add/Mod New Member UI | Input Fields for All Member Details | Text checking on input fields to minimise the chance of invlid data being entered | 5-6 | Rabya | 4
16 | Major | Add/Mod New Member UI | Confirm Button | Button to confirm the member details, checks the inputs then sends it to the member table | 15 | Nic | 2
17 | Critical | Add/Mod New Member UI | Autoincrementing Member ID | When the confirm button is pressed the member ID is automatically generated and added to the database | 16 | Rabya | 2
18 | Major | Add/Mod New Member UI | Viewport to View Members | Snapshot of the member table, needs to be able to be filtered by search interface | 5 | Rabya | 2
19 | Major | Add/Mod New Member UI | Search Input Field | By typing member ID in and confirming, the viewport will display the member searched for (or nothing if no results found) | 18 | Simon | 2
20 | Major | Add/Mod New Member UI | Modify a Member Record | Selecting the searched member result will populate the text fields with saved data. Writing over these with new information and confirming will save over the old record with the new information | 8, 15-19 | Simon | 4
21 | Major | Add/Mod New Item UI | Input Field to Add Item | Text checking on input fields to minimise the chance of invlid data being entered | 1-2 | Dylan | 4
22 | Major | Add/Mod New Item UI | Confirm Button | Pushes item record to the item table | 22 | Thomas | 2
23 | Major | Add/Mod New Item UI | Viewport to View Item | Snapshot of the item table, needs to be able to be filtered by search interface | 1 | Thomas | 2
24 | Major | Add/Mod New Item UI | Search Input Field | By typing item ID in and confirming, the viewport will display the item searched for (or nothing if no results found) | 23 | Thomas | 2
25 | Major | Add/Mod New Item UI | Modify an item Record | Selecting the searched member result will populate the text fields with saved data. Writing over these with new information and confirming will save over the old record with the new information | 4, 21-24 | Nic | 4
[6 empty] | Total | 43.2
Dylan
| Critical |  |  |  |  | Nic
| Major |  |  |  |  | Cody
| Minor |  |  |  |  | Rabya
| Cosmetic |  |  |  |  | Simon
Thomas